## Sheet1
COMPLTED
PENDING
NOT COMPLETED
| Column2 | Column3 | Column4 | Column42 | Column5 | Column53 | Column52 | Column6
IT PROJECT REPORT ON NETWORKS AND INFRASTRUCTURE, HYGEIA HMO.
PREPARED BY: JOHN INALEGWU GABRIEL
| PROJECT NUMBER | PROJECT | START DATE | PURPOSE / REASON | ACCOMPLISHMENT | TOOLS USED TO AID TAKS | COMPLETION DATE | STATUS
| 1 | To configure group policy management on hygeia systems. | MAY, 2019 | Files such as: gpt.ini file; on Network shared folders are not fully replicating between the two domain controllers. | I installed DFRS Role and features. I configured DFRS namespace and replication. Then I force an authoritative DFSR Sync of SYSVOL and NETLOGON folder to fix Group Policy and File Replication | I ran test operations on windows server 2016 and 2012 R2 virtual box comparing the effect of using DFRS over FRS. Research using Youtube media and www.technet.microsoft.com | JUNE, 2019
| 2 | Configure Group policy Object (GPO) Wallpaper on all domain computers | APRIL, 2019 | Wallpaper updates on domain computers to creating awareness/reminder on sales target to assist sales and marketing department | I configured GPOs settings pesonalize Wallpapers on desktop computers; linked through UNC paths on the network and remotely force the updates on all domain computers. | I ran test operations on windows server 2016 and 2012 R2. Research using Youtube media. | JUNE, 2019
| 3 | HYGEIA Laptops and Desktop computers remote maintenance. | MAY, 2018 | To find out how desktops and Laptops can be remotely managed through: systems scan, updates, removable media scan, Network threats (firewall protection) etc. | I configured and deployed Kaspersky Endpoint Security 10 for windows computers and pushed the settings / updates to all domain computers remotely installed and controlled (with administrative rights) on the kaspersky administrative console. | Kaspersky security help center. https://www.kaspersky.com/internet-security | JULY, 2018
| 4 | To restrict USB PORTS access on desktop computers. | SEPTEMBER, 2018 | To restrict unauthorized users access to files stored in Call Center department desktop computers | I restricted USB PORTS access remotely to only Contact Center department destop computers Using Kaspersky Endpoint Security Policy through the Administrative Server Console | Research findings on youtube and kaspersky chat center. | SEPTEMBER, 2018
| 5 | To configure staff files management on the File Server Storage system | MARCH, 2018 | Staffs do store personal video and audio files on the servers's storage drive remotely. | Firstly, I installed File Server Resource Manager (FSRM) role on the File server. I configured Quota and setup File Screening to deny domain users from storing video and audio files on the File Server thereby mantaining server's storage space on the FSRM console. | I ran testing/debug operations on windows server 2016 and 2012 R2 virtual box machine. | MARCH, 2018
6