## Sheet1
COMPLTED
PENDING
NOT COMPLETED
| Column2 | Column3 | Column4 | Column42 | Column5 | Column54 | Column53 | Column52 | Column6
IT PROJECT REPORT ON NETWORKS AND INFRASTRUCTURE, HYGEIA HMO.
PREPARED BY: JOHN INALEGWU GABRIEL
| PROJECT NUMBER | PROJECT | START DATE | PURPOSE / REASON | ACCOMPLISHMENT | PROJECT RESPONSIBILITY | TOOLS USED TO AID TASKs | COMPLETION DATE | STATUS
| 1 | To configure group policy management on hygeia systems. | MAY, 2019 | Files such as: gpt.ini file; on Network shared folders are not fully replicating between the two domain controllers. | I installed DFRS Role and features. I configured DFRS namespace and replication. Then I force an authoritative DFSR Sync of SYSVOL and NETLOGON folder to fix Group Policy and Files not Replicating incidents. | GABRIEL | Windows server 2016 and 2012 R2 on Virtual Box Machines; to compare and test on using DFRS over FRS. Research Media such as: Youtube and www.technet.microsoft.com | JUNE, 2019
| 2 | Configure Group policy Object (GPO) Wallpaper on all domain computers | APRIL, 2019 | Wallpaper updates on domain computers to creating awareness/reminder on sales target to assist sales and marketing department | I configured GPOs settings pesonalize Wallpapers on desktop computers; linked through UNC paths on the network and remotely force the updates on all domain computers. | THE IT TEAM | Windows server 2016 and 2012 R2 on Virtual Box Machines; to compare and test on using DFRS over FRS. Research Media such as: Youtube and www.technet.microsoft.com | JUNE, 2019
| 3 | HYGEIA Laptops and Desktop computers remote maintenance. | MAY, 2018 | To find out how desktops and Laptops can be remotely managed through: systems scan, updates, removable media scan, Network threats (firewall protection) etc. | I configured and deployed Kaspersky Endpoint Security 10 for windows computers and pushed the settings / updates to all domain computers remotely installed and controlled (with administrative rights) on the kaspersky administrative console. | GABRIEL | Kaspersky security help center. https://www.kaspersky.com/internet-security | JULY, 2018
| 4 | To restrict USB PORTS access on desktop computers. | SEPTEMBER, 2018 | To restrict unauthorized users access to files stored in Call Center department desktop computers | I restricted USB PORTS access remotely to only Contact Center department desktop computers Using Kaspersky Endpoint Security Policy, and using Group Policies settings to restrict users from installing Auto-Run Software. | GABRIEL | Youtube media and kaspersky help center. | SEPTEMBER, 2018
| 5 | To configure a means to manage how users / staffs store on the File Server Storage system | MARCH, 2018 | Staffs do store personal video and audio files on the servers's storage drive remotely. | Firstly, I installed File Server Resource Manager (FSRM) role on the File server. I configured Quota and setup File Screening to deny domain users from storing video and audio files on the File Server thereby mantaining server's storage space. | GABRIEL | Windows server 2016 and 2012 R2 on Virtual Box Machines; to compare and test on using DFRS over FRS. Research Media such as: Youtube and www.technet.microsoft.com | MARCH, 2018
| 6 | Integration of Fortigate (ATP) to hygeia network. | OCTOBER, 2018 | Protection against advanced persistent threats (ATP). | Installation of Fortisandbox into the domain network. Installation and configuration of Forticlient Enterprise Management Server on the domain controller. Remote deployment of fortigate security (Forticlient software) installation and configurations to all domain computers on the network. | THE IT TEAM | Windows server 2012 R2 (Secondary Domain Controller) | OCTOBER, 2018
| 7 | To create and share a public folder in microsoft outlook accessible only to authenticated users. | JULY, 2019 | To enable users store their attachments in the public folder, which is accessible to only users given security permissions to in order to manage mailbox storage space. | I was able to create Public Folder mailbox database, configure seurity permissions and setup Public Folder for users to exchange mail attachments. | THE IT TEAM | Microsoft exchange server 2013. | JULY, 2018
| 8 | Migration of 50 Exchange account Users to Office365 account, Setting up and configuration of OneDrive Cloud Storage and backups | AUGUST, 2019 | Migration of Users from Exchange Account to Cloud Office365 Account and Security. | Using Microsoft 365 Admin Center Platform, We were able migrate 50 staff account, setup Onedrive Cloud storage and daily backups of files remotely, configure Group Policy folder redirection on KNOWN computer folders for OneDrive backups to take place. | THE IT TEAM | Microsoft 365 Admin Center, exchange admin center and Group Policy Management tools. | SEPTEMBER, 2019
PLEASE VISIT ON THIS LINK TO SEE SCREENSHOTS OF THE ABOVE PROJECTS UNDERTAKEN https://github.com/Gabieto7/PROJECTS_AS_IT_OFFICER_AT_HYGEIA.git